MAXHUB PVT LTD

# Client proposal - continuous monitoring and control remediation

Next-phase proposal to Mhondoro Manufacturing (Pvt) Ltd following the forensic investigation

Client: Mhondoro Manufacturing (Pvt) Ltd    |    Period: 1 January 2024 to 30 September 2025    |    Issued: 08 October 2025    |    Reference: MX-2025-P01    |    Classification: Confidential

## 1. Your situation, as we understand it

"The Audit Committee received a whistle-blower report. Your investigation found 171 exceptions worth $1,945,536.55, including payments to four suppliers connected to employees and 21 supplier invoices that were paid twice. Nothing in the current process would have caught any of it, and next month the same tests would have to be run again by hand. We want the tests to run themselves, and we want the controls fixed so the exceptions stop happening."

## 2. What you asked us to do

| # | Requirement | Our response |
| --- | --- | --- |
| 1 | Detect this automatically, every month | A twelve-test exception routine running on your own data, delivered as a Power BI dashboard and a monthly report your Financial Controller can use |
| 2 | Fix the controls that failed | Redesigned vendor onboarding and payment approval, a segregation-of-duties matrix and a system access review |
| 3 | Get the money back | A recovery pack for the $184,011.74 of duplicate payments: supplier letters with the evidence attached |
| 4 | Show the board it is working | A quarterly trend pack proving the exception rate is falling |

## 3. Our approach

Phase 1 - Mobilise (week 1). Kick-off, data request list, read-only access, independence and conflict checks, agreement of the exception definitions.

Phase 2 - Data and model (weeks 1-2). Refreshable data layer, star schema, control checks. Nothing is reported until the model reconciles to your trial balance.

Phase 3 - Monitoring build (weeks 2-5). The twelve tests as a scheduled routine; the exception dashboard with drillthrough to the ledger line; the monthly report template.

Phase 4 - Control remediation (weeks 3-6). Process redesign with control points marked, segregation-of-duties matrix, access review, and the system configuration changes your IT team needs to make.

Phase 5 - Recovery and handover (week 6). Recovery pack, board presentation, training for your finance team, handover of every file.

Quality control (week 6). Independent review by a Maxhub partner who did not build the work: re-performance of a calculation, reconciliation of every headline number, language review.

## 4. Deliverables

| # | Deliverable | Format | Week |
| --- | --- | --- | --- |
| 1 | Continuous monitoring model and exception dashboard | .pbix + published app | 5 |
| 2 | Monthly exception report template (populated with your data) | Excel + PDF | 5 |
| 3 | Redesigned vendor onboarding and payment approval process | One-page flow + SOP | 6 |
| 4 | Segregation-of-duties matrix and system access review | Excel + report | 6 |
| 5 | Duplicate-payment recovery pack ($184,011.74) | Letters + evidence schedules | 6 |
| 6 | Board presentation and management training | Slides + session | 6 |
| 7 | Model documentation and user guide | PDF | 6 |

## 5. Team

| Name | Role | Responsibility |
| --- | --- | --- |
| Engagement partner | Partner | Quality control, client relationship, reporting to the Committee |
| T. Makuvaza | Manager | Delivery, model, analysis, board presentation |
| Senior analyst | Senior | Test routine, remediation design |
| Analyst | Analyst | Data preparation, working papers, monthly report |

## 6. Fees

| Item | Basis | Amount (USD) |
| --- | --- | --- |
| Project work, phases 1-6 | 117 hours at Maxhub day rates | 24,760 |
| Continuous monitoring retainer | Monthly, from month 2 | 2,380 / month |
| Training for the finance team | Half day | 1,800 |
| Disbursements | At cost | - |

Billing: 50% on engagement acceptance, 50% on delivery. Fees are exclusive of VAT. Out-of-scope work is quoted before it is performed.

Benchmark: the Service Catalogue prices a Fraud Risk Assessment at $6,000-$18,000 and a Continuous Monitoring retainer at $900-$2,500 per month. This proposal sits inside both ranges: $24,760.00 for the project and $2,380.00 per month.

## 7. Assumptions

You provide the data listed in the data request list in machine-readable form within five working days of kick-off, including the complete creditor sub-ledger (the extract supplied for the investigation was a 520-invoice sample).

One named client contact answers queries within one working day.

The data provided is complete and accurate; we report any indication that it is not.

Your IT team makes the system configuration changes we specify; we do not change your ERP.

Sign-off on drafts within five working days; further revision rounds are chargeable.

Up to six staff interviews of one hour each.

## 8. What is not included

Legal advice, or expert evidence in proceedings (available under a separate engagement).

Tax computations, returns or ZIMRA representation.

Recovering funds on your behalf: we identify, quantify and draft; you or your lawyers pursue.

Changes to your ERP or accounting system.

Data extraction from systems to which you do not give us read-only access.

Audit or assurance opinions. This is advisory work, not an audit.

## 9. Confidentiality and data handling

All client data is confidential, stored only in Maxhub-controlled encrypted locations for the engagement, accessed only by the named engagement team, and returned or destroyed at the end of the retention period (seven years for working papers, 90 days for source data) or earlier on request. Personal data is processed lawfully and minimally in line with Zimbabwe's Cyber and Data Protection Act (2021). Aggregated, de-identified examples may be used for training only with your written permission.

## 10. Why Maxhub

We built the investigation you have just read, so the monitoring is the same work running on a schedule rather than a new team learning your ledger. Every deliverable reconciles to your trial balance before it is issued, and we hand over the model and the documentation - you are never locked in to us.

## 11. Acceptance

| Signed for the client | ______________________ Name / Title / Date |
| --- | --- |
| Signed for Maxhub Pvt Ltd | ______________________ Name / Title / Date |

Prepared by: T. Makuvaza, Engagement Manager    |    Date: 08 October 2025

Reviewed by (independent QC): Independent QC partner (Maxhub)    |    Date: 08 October 2025

This report is confidential and prepared solely for the addressee for the purpose set out in section 1. It may not be relied upon by any other party without Maxhub's written consent. All data analysed is simulated engagement data generated for training purposes.