## Priced scope of work
Project fee built from hours and roles at Maxhub day rates
Phase | Activity | Role | Hours | Rate USD/hr | Fee USD
Phase 1 - Mobilise and data | Data request list, access, integrity checks, reconciliation to the trial balance | Analyst | 8 | 120 | 960
Phase 1 - Mobilise and data | Kick-off, independence and conflict checks | Manager | 3 | 280 | 840
Phase 2 - Model build | Refreshable data layer, star schema, control checks | Senior | 16 | 200 | 3200
Phase 3 - Continuous monitoring | Twelve-test exception routine on the client's own data, monthly | Senior | 24 | 200 | 4800
Phase 3 - Continuous monitoring | Power BI exception dashboard and drillthrough | Senior Analyst | 20 | 150 | 3000
Phase 4 - Control remediation | Redesigned vendor onboarding and payment approval process, documented with control points | Manager | 12 | 280 | 3360
Phase 4 - Control remediation | System access review and segregation-of-duties matrix | Senior | 8 | 200 | 1600
Phase 5 - Recovery support | Duplicate-payment recovery pack: supplier letters, evidence schedules | Senior Analyst | 10 | 150 | 1500
Phase 6 - Reporting and handover | Board presentation, management training, handover of all files | Manager | 10 | 280 | 2800
Quality control | Independent partner review: re-performance, reconciliation, language | Partner | 6 | 450 | 2700
**Total** |  |  | 117 |  | 24760

## Retainer
Continuous monitoring retainer
Monthly activity | Role | Hours | Rate USD/hr | Fee USD
Monthly exception report from the client's own data (12 tests) | Senior Analyst | 6 | 150 | 900
Review of exceptions with the Financial Controller (60 minutes) | Senior | 2 | 200 | 400
Refresh monitoring and data-quality checks | Analyst | 2 | 120 | 240
Quarterly control review and trend commentary | Manager | 3 | 280 | 840
**Total per month** |  | 13 |  | 2380

## Rate card and benchmark
Maxhub rate card and catalogue benchmarks
Role | Hourly rate USD | Day rate (8h) USD | Catalogue benchmark
Analyst | 120 | 960 | Data analytics engagement $6,000-$18,000
Senior Analyst | 150 | 1200 | Analytics foundation $4,000-$15,000
Senior | 200 | 1600 | Working capital analytics $3,000-$9,000
Manager | 280 | 2240 | Forensic investigation $8,000-$45,000
Partner | 450 | 3600 | IFRS technical support $300-$1,200/day

## Value case
The commercial case, stated honestly
Item | Amount USD | Basis
Duplicate payments recoverable | 184011.74 | Second payment of each of the 21 duplicate pairs
Total amount at risk | 1761524.81 | Exceptions requiring corroboration
Payments to employee-linked vendors | 2773799.2 | Total paid; propriety requires corroboration
Year 1 cost of this engagement | 50940 | Project fee plus 11 months of retainer
Net benefit if only the duplicates are recovered | 133071.74 | Recovery less cost - before any control benefit