## Anomaly register
Engagement-economics anomalies - 52 of 96 delivered engagements
Over-run > 25% of planned hours; write-off > 15% of fee; negative contribution margin; realisation < 70% of standard rate. Severity = write-offs + over-run hours at the standard rate + the value of any negative margin. Every anomaly needs the one-line explanation completing before the partner meeting.
Rank | Engagement | Client | Service line | Manager | Period | Status | Planned hours | Actual hours | Over-run % | Fee USD | Write-off USD | Realisation % | Margin % | NPS | Severity USD | Anomaly | Explanation (partner to complete)
1 | MX-20240120 | Great Dyke Mining | Forensic investigation | J. Marufu | 2024-02 | Completed | 80 | 411.9326 | 414.9% | 10491.63 | 108.61 | 9.1% | -395.7% | 10 | 134570.24 | Over-ran budget by 415%; Negative margin -396%; Realisation 9%
2 | MX-20250045 | Mhondoro Manufacturing | Machine learning model | T. Makuvaza | 2025-08 | Completed | 40 | 440.7329 | 1002% | 135304.78 | 0 | 118.1% | 61.9% | 7 | 104190.56 | Over-ran budget by 1002%
3 | MX-20240024 | UnivTrust Procurement | IFRS advisory | T. Makuvaza | 2024-02 | Completed | 40 | 449.2053 | 1023% | 67151.59 | 0 | 65% | 30.8% | 6 | 94117.22 | Over-ran budget by 1023%; Realisation 65%
4 | MX-20240010 | FoodProcessors Alliance | Power BI dashboard | S. Moyo | 2024-07 | In progress | 40 | 443.9029 | 1010% | 25499.86 | 0 | 30.2% | -48.8% | 9 | 89195.4 | Over-ran budget by 1010%; Negative margin -49%; Realisation 30%
5 | MX-20240074 | FoodProcessors Alliance | Forensic investigation | T. Makuvaza | 2024-12 | Completed | 120 | 274.2438 | 128.5% | 10607.94 | 0 | 13.8% | -225.7% | 10 | 67135.03 | Over-ran budget by 129%; Negative margin -226%; Realisation 14%
6 | MX-20240058 | RetailZ Supermarkets | Data analytics build | S. Moyo | 2024-08 | Completed | 120 | 399.2656 | 232.7% | 77725.17 | 10953.67 | 97.3% | 39.7% | 10 | 66806.8 | Over-ran budget by 233%
7 | MX-20250150 | AgriHub Cooperative | Fraud risk assessment | J. Marufu | 2025-04 | In progress | 24 | 275.3141 | 1047% | 72201.09 | 0 | 104.9% | 57.1% | 9 | 62828.53 | Over-ran budget by 1047%
8 | MX-20250088 | Great Dyke Mining | IFRS advisory | T. Makuvaza | 2025-06 | Completed | 24 | 231.2978 | 863.7% | 12954.41 | 0 | 24.4% | -84.8% | 9 | 58663.4 | Over-ran budget by 864%; Negative margin -85%; Realisation 24%
9 | MX-20240034 | UnivTrust Procurement | IFRS advisory | S. Moyo | 2024-09 | Completed | 120 | 261.3756 | 117.8% | 4218.12 | 0 | 7% | -541.3% | 7 | 55350.64 | Over-ran budget by 118%; Negative margin -541%; Realisation 7%
10 | MX-20250090 | FoodProcessors Alliance | Data analytics build | J. Marufu | 2025-05 | Completed | 24 | 274.4086 | 1043% | 45372.89 | 0 | 82.7% | 45.6% | 9 | 50081.72 | Over-ran budget by 1043%
11 | MX-20240104 | Mhondoro Manufacturing | Fraud risk assessment | J. Marufu | 2024-04 | Completed | 120 | 297.1756 | 147.6% | 83082.1 | 2010.18 | 111.8% | 57.3% | 6 | 46304.07 | Over-ran budget by 148%
12 | MX-20250136 | Mhondoro Manufacturing | Tax analytics | J. Marufu | 2025-01 | In progress | 24 | 281.1465 | 1071% | 131645.1 | 0 | 260.1% | 82.7% | 8 | 46286.36 | Over-ran budget by 1071%
13 | MX-20240001 | SADC Industrial Supplies | Fraud risk assessment | T. Makuvaza | 2024-04 | In progress | 320 | 422.5966 | 32.1% | 29417 | 0 | 27.8% | -61.6% | 7 | 43774.28 | Over-ran budget by 32%; Negative margin -62%; Realisation 28%
14 | MX-20240063 | Great Dyke Mining | IFRS advisory | T. Makuvaza | 2024-04 | Completed | 40 | 224.371 | 460.9% | 47772.45 | 0 | 92.6% | 51.4% | 10 | 42405.32 | Over-ran budget by 461%
15 | MX-20250107 | FoodProcessors Alliance | Fraud risk assessment | J. Marufu | 2025-08 | Completed | 40 | 208.7901 | 422% | 50057.48 | 0 | 95.9% | 53.1% | 9 | 42197.53 | Over-ran budget by 422%
16 | MX-20240158 | RetailZ Supermarkets | Fraud risk assessment | T. Makuvaza | 2024-08 | Completed | 24 | 180.0138 | 650.1% | 24866.15 | 203.75 | 55.3% | 17.7% | 10 | 39207.2 | Over-ran budget by 650%; Realisation 55%
17 | MX-20250039 | UnivTrust Procurement | Forensic investigation | J. Marufu | 2025-08 | In progress | 320 | 303.917 | -5% | 3869.28 | 0 | 4.5% | -889.7% | 8 | 34424.27 | Negative margin -890%; Realisation 5%
18 | MX-20250007 | Great Dyke Mining | Tax analytics | T. Makuvaza | 2025-04 | Completed | 120 | 282.3862 | 135.3% | 27047.95 | 2201.41 | 53.2% | 7.3% | 10 | 31430.92 | Over-ran budget by 135%; Realisation 53%
19 | MX-20240153 | Sunrise Hospitals | Machine learning model | S. Moyo | 2024-07 | Completed | 40 | 160.4412 | 301.1% | 68675.43 | 0 | 164.6% | 72.7% | 9 | 31314.72 | Over-ran budget by 301%
20 | MX-20250109 | SADC Industrial Supplies | Power BI dashboard | T. Makuvaza | 2025-08 | Completed | 80 | 241.7205 | 202.2% | 40056.72 | 0 | 87.2% | 48.4% | 6 | 30726.89 | Over-ran budget by 202%
21 | MX-20240040 | UnivTrust Procurement | Forensic investigation | S. Moyo | 2024-02 | In progress | 120 | 167.3995 | 39.5% | 9424.48 | 1665.64 | 20.1% | -141.5% | 6 | 28271.01 | Over-ran budget by 39%; Write-off 18% of fee; Negative margin -141%; Realisation 20%
22 | MX-20250052 | Municipality of Kadoma | Power BI dashboard | J. Marufu | 2025-01 | Completed | 320 | 362.6615 | 13.3% | 16732.29 | 2838.62 | 24.3% | -102.3% | 6 | 28058.18 | Write-off 17% of fee; Negative margin -102%; Realisation 24%
23 | MX-20240055 | UnivTrust Procurement | Forensic investigation | T. Makuvaza | 2024-07 | Completed | 40 | 137.9656 | 244.9% | 85591.75 | 0 | 221.6% | 79.7% | 6 | 27430.37 | Over-ran budget by 245%
24 | MX-20250156 | Mhondoro Manufacturing | Data analytics build | S. Moyo | 2025-04 | In progress | 24 | 125.7297 | 423.9% | 9529.04 | 1249.34 | 37.9% | -31.9% | 6 | 24631.24 | Over-ran budget by 424%; Negative margin -32%; Realisation 38%
25 | MX-20240002 | Sunrise Hospitals | IFRS advisory | T. Makuvaza | 2024-03 | Completed | 200 | 302.6364 | 51.3% | 49728.35 | 0 | 71.4% | 37% | 8 | 23606.38 | Over-ran budget by 51%
26 | MX-20250131 | FoodProcessors Alliance | Fraud risk assessment | J. Marufu | 2025-01 | Completed | 24 | 113.8432 | 374.3% | 45897.09 | 0 | 161.3% | 72.1% | 10 | 22460.79 | Over-ran budget by 374%
27 | MX-20240021 | FoodProcessors Alliance | IFRS advisory | T. Makuvaza | 2024-09 | Completed | 120 | 201.1932 | 67.7% | 32122.27 | 0 | 69.4% | 35.2% | 8 | 18674.44 | Over-ran budget by 68%; Realisation 69%
28 | MX-20240023 | RetailZ Supermarkets | Tax analytics | J. Marufu | 2024-04 | Completed | 80 | 182.2841 | 127.9% | 45241.87 | 0 | 137.9% | 67.4% | 9 | 18411.14 | Over-ran budget by 128%
29 | MX-20240050 | Sunrise Hospitals | CFO advisory retainer | T. Makuvaza | 2024-05 | Completed | 320 | 280.7767 | -12.3% | 8387.72 | 35.26 | 14.2% | -216.8% | 9 | 18216.2 | Negative margin -217%; Realisation 14%
30 | MX-20250022 | UnivTrust Procurement | Power BI dashboard | J. Marufu | 2025-01 | Completed | 40 | 131.5974 | 229% | 10465.98 | 0 | 41.9% | -7.5% | 6 | 18189.1 | Over-ran budget by 229%; Negative margin -8%; Realisation 42%
31 | MX-20250081 | RetailZ Supermarkets | Internal audit co-sourcing | S. Moyo | 2025-08 | Completed | 120 | 226.454 | 88.7% | 49302.59 | 0 | 128.1% | 64.9% | 10 | 18097.18 | Over-ran budget by 89%
32 | MX-20250018 | FoodProcessors Alliance | Tax analytics | J. Marufu | 2025-09 | Completed | 24 | 109.2988 | 355.4% | 15498.31 | 1798.57 | 78.8% | 31.3% | 9 | 17152.35 | Over-ran budget by 355%
33 | MX-20240097 | Mhondoro Manufacturing | Data analytics build | T. Makuvaza | 2024-09 | In progress | 320 | 262.6895 | -17.9% | 8316.92 | 248.06 | 15.8% | -187.2% | 9 | 15821.25 | Negative margin -187%; Realisation 16%
34 | MX-20250096 | SADC Industrial Supplies | Machine learning model | J. Marufu | 2025-03 | In progress | 200 | 211.2107 | 5.6% | 76380.18 | 11670.99 | 139.1% | 52.4% | 6 | 14585.76 | Write-off 15% of fee
35 | MX-20250048 | AgriHub Cooperative | CFO advisory retainer | J. Marufu | 2025-08 | In progress | 24 | 81.9084 | 241.3% | 49039.51 | 0 | 285.1% | 84.2% | 9 | 12160.76 | Over-ran budget by 241%
36 | MX-20250046 | TransContinental Haulage | CFO advisory retainer | T. Makuvaza | 2025-01 | Completed | 40 | 97.0915 | 142.7% | 10340.43 | 0 | 50.7% | 11.3% | 8 | 11989.21 | Over-ran budget by 143%; Realisation 51%
37 | MX-20240030 | TransContinental Haulage | Data analytics build | T. Makuvaza | 2024-03 | Completed | 80 | 132.5361 | 65.7% | 124303.3 | 0 | 468.9% | 90.4% | 9 | 10507.23 | Over-ran budget by 66%
38 | MX-20250042 | AgriHub Cooperative | CFO advisory retainer | T. Makuvaza | 2025-06 | In progress | 40 | 80.8711 | 102.2% | 29444.17 | 474.31 | 173.4% | 72.4% | 9 | 9057.24 | Over-ran budget by 102%
39 | MX-20240140 | AgriHub Cooperative | Power BI dashboard | S. Moyo | 2024-04 | In progress | 200 | 205.7636 | 2.9% | 10623.47 | 491.75 | 27.2% | -70.2% | 6 | 9047.89 | Negative margin -70%; Realisation 27%
40 | MX-20250061 | Municipality of Kadoma | IFRS advisory | S. Moyo | 2025-04 | In progress | 120 | 152.1878 | 26.8% | 42029.98 | 0 | 120.1% | 62.5% | 9 | 7403.19 | Over-ran budget by 27%
41 | MX-20250125 | Great Dyke Mining | Data analytics build | J. Marufu | 2025-01 | In progress | 200 | 112.8871 | -43.6% | 4074.36 | 96.77 | 18% | -151.7% | 7 | 6279.01 | Negative margin -152%; Realisation 18%
42 | MX-20240114 | Sunrise Hospitals | Machine learning model | J. Marufu | 2024-12 | In progress | 200 | 220.5528 | 10.3% | 39293.62 | 0 | 68.5% | 34.3% | 9 | 5343.74 | Realisation 69%
43 | MX-20240057 | Sunrise Hospitals | Fraud risk assessment | T. Makuvaza | 2024-01 | In progress | 80 | 99.391 | 24.2% | 13930.9 | 0 | 56.1% | 19.7% | 10 | 4847.74 | Realisation 56%
44 | MX-20250043 | UnivTrust Procurement | Tax analytics | T. Makuvaza | 2025-05 | Completed | 320 | 155.2667 | -51.5% | 8401.79 | 0 | 30.1% | -49.7% | 10 | 4174.81 | Negative margin -50%; Realisation 30%
45 | MX-20250143 | Municipality of Kadoma | Fraud risk assessment | S. Moyo | 2025-04 | In progress | 200 | 211.061 | 5.5% | 25402.17 | 0 | 48.1% | 6.5% | 9 | 2765.26 | Realisation 48%
46 | MX-20240148 | FoodProcessors Alliance | IFRS advisory | S. Moyo | 2024-01 | Completed | 24 | 34.6414 | 44.3% | 4387.22 | 0 | 55.1% | 18.3% | 9 | 2447.51 | Over-ran budget by 44%; Realisation 55%
47 | MX-20240134 | SADC Industrial Supplies | CFO advisory retainer | S. Moyo | 2024-03 | Completed | 80 | 23.4002 | -70.7% | 10144.61 | 1552.84 | 206.4% | 62.9% | 10 | 1552.84 | Write-off 15% of fee
48 | MX-20240126 | Mhondoro Manufacturing | Internal audit co-sourcing | T. Makuvaza | 2024-07 | Completed | 200 | 137.7432 | -31.1% | 14375.65 | 1298.41 | 61.4% | 17.7% | 9 | 1298.41 | Realisation 61%
49 | MX-20250005 | TransContinental Haulage | Internal audit co-sourcing | J. Marufu | 2025-04 | Completed | 320 | 43.0102 | -86.6% | 4483.72 | 492.15 | 61.3% | 15.6% | 10 | 492.15 | Realisation 61%
50 | MX-20240082 | Great Dyke Mining | Data analytics build | J. Marufu | 2024-02 | Completed | 120 | 120.9453 | 0.8% | 15784.14 | 0 | 65.3% | 31% | 7 | 189.05 | Realisation 65%
51 | MX-20250117 | Great Dyke Mining | Power BI dashboard | J. Marufu | 2025-04 | Completed | 320 | 109.9392 | -65.6% | 9389.3 | 0 | 44.9% | -0.1% | 9 | 10.5 | Negative margin -0%; Realisation 45%
52 | MX-20240025 | SADC Industrial Supplies | Fraud risk assessment | T. Makuvaza | 2024-05 | Completed | 40 | 37.7416 | -5.6% | 4356.06 | 0 | 46.2% | 2.5% | 9 | 0 | Realisation 46%

## Summary
Anomaly summary
An exception rate above half is itself the finding: engagement economics are not being monitored, so over-runs are discovered at invoicing rather than in month one.
Measure | Value
Delivered engagements tested | 96
Engagements excluded (proposal or lost) | 64
Anomalies raised | 52
Exception rate | 0.5417
Total write-offs in the exception set | 39390.33
Severity in the top 25 | 1303008.28
Thresholds | Over-run > 25% of planned hours; write-off > 15% of fee; negative contribution margin; realisation < 70% of standard rate.